## Cash Flow
[23 empty] | Site Details | [10 empty] | PROGRAMME AND CASH FLOW PROJECTION | [46 empty] | Beaconstone, Hillcommon, Taunton, Somerset, TA4 1DU
01823 400480
enquiries@est-e-mate.co.uk
www.est-e-mate.co.uk
| Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 | Week 20 | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26 | Week 27 | Week 28
Commencement | 1 | 1 | 1 | 1 | 1
Site set up | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Foundations | [5 empty] | 1 | 1 | 1 | 1 | 1
Footings | [8 empty] | 1 | 1
Oversite and slabbing | [10 empty] | 1 | 1 | 1 | 1 | 1
Brickwork Shell | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Erect Scaffold | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
First Floor Joists | [30 empty] | 1 | 1 | 1 | 1 | 1
Roof Structure | [40 empty] | 1 | 1 | 1 | 1 | 1
Roof Tiling | [45 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Joinery 1st Fix | [55 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Plastering | [65 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Joinery 2nd Fix | [76 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Internal Decoration | [88 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
External Decoration | [98 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cleaning | [103 empty] | 1 | 1 | 1 | 1 | 1
Completion | [108 empty] | 1 | 1 | 1 | 1 | 1
Value of work completed on site
Labour | 204 |  |  |  |  | 1585.07 |  |  |  |  | 699.08 |  |  |  |  | 1258.69 |  |  |  |  | 1258.69 |  |  |  |  | 1258.69 |  |  |  |  | 1258.69 |  |  |  |  | 1258.69 |  |  |  |  | 4201.35 |  |  |  |  | 1175.16 |  |  |  |  | 1175.17 |  |  |  |  | 918.05 |  |  |  |  | 918.06 |  |  |  |  | 5432.25 |  |  |  |  | 5432.25 | [5 empty] | 1257.95 |  |  |  |  | 1257.94 | [6 empty] | 1413.14 |  |  |  |  | 1413.13 |  |  |  |  | 927.54 |  |  |  |  | 150 |  |  |  |  | 130
Materials | 132 |  |  |  |  | 3387.49 |  |  |  |  | 2945.81 |  |  |  |  | 8513.75 |  |  |  |  | 8513.75 | [19 empty] | 5203.12 |  |  |  |  | 3423.69 | [9 empty] | 3120.61 | [9 empty] | 7712.58 | [10 empty] | 2796.05 | [11 empty] | 620.22 | [9 empty] | 218.7
Plant | 1591.17 |  |  |  |  | 2125.93 |  |  |  |  | 63 | [14 empty] | 950 | [9 empty] | 950 | [19 empty] | 20 | [9 empty] | 22
Provisional sums | 2000 |  |  |  |  | 1750 | [14 empty] | 1000 | [19 empty] | 10000 | [14 empty] | 375 | [9 empty] | 4750 | [9 empty] | 6500 | [5 empty] | 1500 |  |  |  |  | 2000 | 4750 | 750 |  |  |  |  | 4500 | [14 empty] | 3850
VAT | 744.634 |  |  |  |  | 1452.684 |  |  |  |  | 601.762 |  |  |  |  | 1702.75 |  |  |  |  | 1902.75 |  |  |  |  | 190 | [9 empty] | 190 |  |  |  |  | 3040.624 |  |  |  |  | 684.738 | [9 empty] | 703.122 | [9 empty] | 2496.916 | [9 empty] | 1300 | 559.21 |  |  |  |  | 300 |  |  |  |  | 400 | 950 | 274.044 |  |  |  |  | 900 |  |  |  |  | 43.74 | [9 empty] | 770
TOTAL | 4671.804 |  |  |  |  | 10301.174 |  |  |  |  | 4309.652 |  |  |  |  | 11475.19 |  |  |  |  | 12675.19 |  |  |  |  | 2398.69 |  |  |  |  | 1258.69 |  |  |  |  | 2398.69 |  |  |  |  | 22445.094 |  |  |  |  | 5283.588 |  |  |  |  | 1175.17 |  |  |  |  | 5136.782 |  |  |  |  | 918.06 |  |  |  |  | 20413.746 |  |  |  |  | 5432.25 |  |  |  |  | 7800 | 4613.21 |  |  |  |  | 3057.94 |  |  |  |  | 2400 | 5700 | 3057.404 |  |  |  |  | 6813.13 |  |  |  |  | 1189.98 |  |  |  |  | 150 |  |  |  |  | 4750
Payments Out | [15 empty] | 3746.84 | [19 empty] | 32045.74 | [19 empty] | 21166.23 | [19 empty] | 38353.464 | [11 empty] | 25297.386 | [15 empty] | 17159.07 | [11 empty] | 12056.704
VAT Refund | [76 empty] | -11213.064 | [36 empty] | -7993.91
Cumulative Cash Flow | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | -3746.84 |  |  |  |  | -3746.84 |  |  |  |  | -3746.84 |  |  |  |  | -3746.84 |  |  |  |  | -35792.58 |  |  |  |  | -35792.58 |  |  |  |  | -35792.58 |  |  |  |  | -35792.58 |  |  |  |  | -56958.81 |  |  |  |  | -56958.81 |  |  |  |  | -56958.81 |  |  |  |  | -56958.81 |  |  |  |  | -95312.274 | -84099.21 |  |  |  |  | -84099.21 |  |  |  |  | -84099.21 | -109396.596 | -109396.596 |  |  |  |  | -109396.596 |  |  |  |  | -109396.596 |  |  |  |  | -126555.666 |  |  |  |  | -126555.666 |  |  |  |  | -118561.756 | -118561.756 | -130618.46
USER GUIDE
If you would like to change any of the blocks on the Program Of Works, you can do so by simply entering the number 1 in any square, it will then automatically change to the preset colour of that line.
To remove a highlighted square, click on the square and hit delete on the keyboard.
To edit a figure in the Cash Flow Projection, simply highlight the square containing the figure, and type the new number. Squares that contain formula have been locked for editing to ensure the document is self-calculating
If you have any questions or require any assistance whilst editing this document, please feel free to contact Jordan Priddle by email: jordan.priddle@est-e-mate.co.uk or telephone: 01823 400480

## BuildPhaseList - Hide This! (hidden)
[5 empty] | > |  | < | > |  |  | <
Master Build Phase List |  | Your Build Phase List
Pos. | Build Phase Header | Build Phase Pos. |  | Your Build Phase Order | Checks |  |  |  | Look Ups
| Additional Floor Joists | Build Phase | 1 | Commencement | Check 1 | 0 | No Error |  | 1 | 1
6 | Brickwork Shell | Build Phase | 2 | Site set up | Check 2 | 0 | No Error |  | 2 | 3
| Building Regulations | Build Phase | 3 | Foundations |  |  |  |  | 3 | 6
16 | Cleaning | Build Phase | 4 | Footings |  |  |  |  | 4 | 10
1 | Commencement | Build Phase | 5 | Oversite and slabbing |  |  |  |  | 5 | 15
17 | Completion | Build Phase | 6 | Brickwork Shell |  |  |  |  | 6 | 21
| Demolition | Build Phase | 7 | Erect Scaffold |  |  |  |  | 7 | 28
| Design Phase | Build Phase | 8 | First Floor Joists |  |  |  |  | 8 | 36
| Drains | Build Phase | 9 | Roof Structure |  |  |  |  | 9 | 45
| Electrician 1st Fix | Build Phase | 10 | Roof Tiling |  |  |  |  | 10 | 55
| Electrician 2nd Fix | Build Phase | 11 | Joinery 1st Fix |  |  |  |  | 11 | 66
7 | Erect Scaffold | Build Phase | 12 | Plastering |  |  |  |  | 12 | 78
15 | External Decoration | Build Phase | 13 | Joinery 2nd Fix |  |  |  |  | 13 | 91
| External Preparation | Build Phase | 14 | Internal Decoration |  |  |  |  | 14 | 105
| External Works 1 | Build Phase | 15 | External Decoration |  |  |  |  | 15 | 120
| External Works 2 | Build Phase | 16 | Cleaning |  |  |  |  | 16 | 136
| External Works 3 | Build Phase | 17 | Completion |  |  |  |  | 17 | 153
8 | First Floor Joists | Build Phase | 18 | [5 empty] | 18 | 171
4 | Footings | Build Phase | 19 | [5 empty] | 19 | 190
3 | Foundations | Build Phase | 20 | [5 empty] | 20 | 210
| Ground Floor Joists | Build Phase | 21 | [5 empty] | 21 | 231
14 | Internal Decoration | Build Phase | 22 | [5 empty] | 22 | 253
| Internal Fitting Out | Build Phase | 23 | [5 empty] | 23 | 276
| Internal Preparation | Build Phase | 24 | [5 empty] | 24 | 300
11 | Joinery 1st Fix | Build Phase | 25 | [5 empty] | 25 | 325
13 | Joinery 2nd Fix | Build Phase | 26 | [5 empty] | 26 | 351
| Landscaping | Build Phase | 27 | [5 empty] | 27 | 378
| Main Drains | Build Phase | 28 | [5 empty] | 28 | 406
5 | Oversite and slabbing | Build Phase | 29 | [5 empty] | 29 | 435
| Planning Application | Build Phase | 30 | [5 empty] | 30 | 465
12 | Plastering | Build Phase | 31 | [5 empty] | 31 | 496
| Plumb 1st Fix | Build Phase | 32 | [5 empty] | 32 | 528
| Plumb 2nd Fix | Build Phase | 33 | [5 empty] | 33 | 561
| Post Contract | Build Phase | 34 | [5 empty] | 34 | 595
| Precontract | Build Phase | 35 | [5 empty] | 35 | 630
| Roads 1 | Build Phase | 36 | [5 empty] | 36 | 666
| Roads 2 | Build Phase | 37 | [5 empty] | 37 | 703
9 | Roof Structure | Build Phase | 38 | [5 empty] | 38 | 741
10 | Roof Tiling | Build Phase | 39 | [5 empty] | 39 | 780
| Site Acquisition | Build Phase | 40 | [5 empty] | 40 | 820
2 | Site set up | Build Phase | 41 | [5 empty] | 41 | 861
| Structural Openings | Build Phase | 42 | [5 empty] | 42 | 903
| Timber Frame | Build Phase | 43 | [5 empty] | 43 | 946
| Underpinning | Build Phase | 44 | [5 empty] | 44 | 990
Note on K4: This checks if the number of build pahses in the "Your Build Phase Order" list is equal to the number of entries in the "Pos." column in the "Master Build Phase List" section.
Note on K5: This checks if the sum of the numbers in the "Pos." column correctly relate to the number of numbers in the "Pos." column.